## Engagement
Engagement scoping intake
Complete with the target owner and tester. Link the authorized scope and RoE before testing; this form grants no permission.
Decision or context | Response / record reference | What to capture
Engagement ID and version | EXAMPLE-01 / draft 1 | Use the adopting organization’s record identifier.
Objective and relying decision | Can a customer read another customer’s synthetic order? | What question will this test answer, and who will use the result?
Target or service name | Orders API (fictional) | Name the system; record precise components on Scope objects.
Business function and critical workflows | Retrieve an order by ID in the v2 API | Summarize what the target does and the workflows that matter.
Target owner and decision contact | Product owner / local directory | Name roles or controlled-directory references; avoid private contact details in a public example.
Technical and operational contacts | API architect and operations contact / local directory | Include the person who can explain architecture and the person who can respond to disruption.
Testing representative | Test lead / local directory | The scoping participant, not the authorizer by implication.
Testing perspective | Supplied-credential, two customer identities | For example, unauthenticated, supplied-credential, code-assisted, or a declared combination.
Target surfaces | API | Web, API, mobile, client, mainframe, cloud, network, data, physical, AI, or other.
Environments and versions | Staging build 2.4; production excluded | Name production and nonproduction separately; identify build or release.
Third-party and shared-service boundaries | Payment provider excluded; identity service is a named dependency | Name owners and any separate permission needed.
Data classes and test-data plan | Two synthetic customer records only | Use synthetic or approved data; record handling conditions in the RoE.
Architecture and interface references | Sanitized API definition in local record | Link current diagrams, API definitions, build details, or repository references through the local record system.
Requested coverage and known limits | One retrieval workflow and two identities; no production inference | State depth/breadth and any question that available access cannot answer.
Scope decision record and version | Pending owner authorization; example is not approved scope | Reference the authorized scope decision. This workbook does not grant permission.
Linked rules of engagement and version | Pending local RoE decision | §10.2 or the adopting organization’s equivalent.
Open scoping decisions | Second account and proof limit remain open | Name the decision owner and unresolved question; do not treat blank as approval.

## Scope objects
Scope objects
One row per material target, workflow, identity, or dependency. IN, OUT, and CONDITIONAL are proposed boundary states until approved elsewhere.
Surface | Exact target or workflow | Environment / version | Identity context | Boundary state | Owner / permission reference | Dependency or exclusion | Evidence question | Decision / change reference
API | GET /orders/{id} | Staging / 2.4 | Customer A and B | CONDITIONAL | Product owner / pending | Payment provider OUT | Can A read B’s synthetic order? | Pending scope decision
Service | Payment provider | External service | None | OUT | Separate provider | No calls or data transfer | Not assessed | Explicit exclusion
API | Production orders API | Production | None | OUT | Product owner | No production access | Not assessed | Explicit exclusion

## Surface prompts
Surface prompts
Use only applicable prompts. Write N/A with a reason where a selected surface does not apply. Copy a prompt into the local scope or RoE decision as needed.
Surface | Question | Response / reference | Scope or RoE decision needed
All | What exact component, environment, build, and workflow are in scope? | Staging v2 retrieval workflow only | Exact endpoint and version in scope record
All | Who owns the target, data, identity provider, and connected services? | Product owner controls API; provider separate | Provider path excluded
All | Which user or service roles are needed for meaningful contrast? | Two synthetic customer identities required | Second account outstanding
All | What is explicitly out of scope or conditional?
All | Which diagrams, interface descriptions, or source references are current?
All | What approved data, monitoring, stop contact, and safe test window are needed?
Web / API | Which URLs, routes, API versions, methods, and resource types are relevant? | v2 order retrieval only | One endpoint; other methods excluded
Web / API | Which authentication and authorization flows and test identities are available? | Two supplied customer accounts | Authorization contrast planned
Web / API | Can a sanitized request collection or interface definition be supplied? | Sanitized API definition in local record | No secrets in workbook
Web / API | Are GraphQL, asynchronous events, gateways, throttling, or downstream effects relevant? | Gateway rate cap to be set in RoE | Testing waits on RoE decision
Mobile / client | Which platforms, signed builds, local components, update paths, and backend APIs are included?
Mobile / client | What devices, test builds, accounts, and permitted instrumentation are available?
Mobile / client | Which app protections or SDKs affect test setup and need separate approval?
Infrastructure / cloud | Which accounts, tenants, regions, hosts, clusters, roles, and control planes are included?
Data platform | Which engines, instances, schemas, roles, interfaces, and data boundaries are included?
Legacy / mainframe | Which platform, partition, application, access path, role, and database are included?
Legacy / mainframe | Who can provide approved test identities, access, and operational support?
Physical | Which facility, zones, people, safety boundaries, and separate authorities apply?
AI target | Which model-facing app, retrieval source, tool, identity, and downstream action are in scope?
AI used by tester | Is an AI tool proposed for the test? If so, what capability, data, action, and human checkpoints are approved in the RoE?
All | What material uncertainty or missing prerequisite changes the answer the test can support?

## Prerequisites
Prerequisites
Record access and setup needs. Never place passwords, tokens, private keys, or live sensitive data in this workbook. Use an approved secure handoff.
Prerequisite | Why needed | Provider / owner | State | Secure handoff or record reference | If unavailable / decision needed
Second customer account | Cross-customer contrast | Product owner | REQUESTED | Approved vault reference pending | If absent, isolation question remains untested
Synthetic order data | Avoid live customer data | Data owner | AVAILABLE | Local controlled dataset reference | Use only approved synthetic records
Rate and stop conditions | Avoid unintended impact | Operations / authorizer | NEEDED | RoE decision pending | Do not start affected test

## Change decisions
Change decisions
A newly discovered target or changed condition waits for the authorized local decision. Record the decision and update the signed scope and RoE as needed.
Change ID | Affected object | New fact / question | Proposed boundary | Decision owner | Decision / date | Linked scope / RoE version
C-01 | Second account | Only one customer role supplied | Keep cross-customer test conditional | Product owner | Pending | Draft scope / RoE